# Life of Jesus — 60-Day Promotion & SEO Plan

For: Phil Cheevers & Pierre

Brand: Life of Jesus sacred art coloring books

Live store: https://www.lifeofjesus.ca/

Comfort site (testbed): https://pinkhouse.tech/lifeofjesus/

Plan window: ~60 days from early August 2026 through late September 2026

Goal: Get eyeballs on the new comfort-first site, finish the SEO foundation, and sell books/bundles — especially into fall gift season and Canadian parish channels.

# How to put this on your laptop (C: drive)

Cloud agents cannot write directly to your Windows `C:\` drive. Use this path:

Open the pull request for this document on GitHub.

Download `lifeofjesus/60-DAY-PROMOTION-AND-SEO-PLAN.docx` (easiest to open in Word / upload to Google Docs).

Save it somewhere simple, for example:

`C:\LifeOfJesus\60-DAY-PROMOTION-AND-SEO-PLAN.docx`

Optional: upload that same file to Google Drive → Open with Google Docs for phone reading.

A markdown twin of this file sits beside the Word file in the same folder.

# 1. The strategy we are extending (in plain English)

You already built the hard part: a quiet gallery for a comfort gift, not a hard-sell catalog.

| Pillar | What it means for the next 60 days |
| --- | --- |
| Comfort first, shop second | Ads, pins, and emails should lead with art + story, then one clear Buy / Gift link. |
| Brand as the hero | Say Life of Jesus first. Don’t lead with “coloring book store.” |
| Canada + churches first | Ontario / Canadian parish proof is your unfair advantage. Use it. |
| Seasonal gifts | August–September prepares Christmas and Advent gift buying. Plant now so December harvests. |
| SEO is a foundation, not the whole harvest | Fix technical SEO and add useful pages — but sales in 60 days will come more from churches, gifts, and beautiful art content than from Google alone. |
| Study guide = trust asset | Free sample on the site; full guide with purchase. Helps pastors evaluate before ordering. |

North-star outcome for these 60 days:

More people land on a comfort-first page → linger with the art → buy the $39.99 book or a bundle — or a parish emails Pierre about fundraising.

# 2. The SEO scoop (what it is, what we do)

## What SEO actually means for Life of Jesus

SEO = helping Google (and people sharing links) understand:

Who you are — Life of Jesus, Canadian sacred-art coloring books

What to show — cover image, title, short description, maybe price

Which pages matter — home, book, shop, about, study guide

That the site is trustworthy — real proof, clear contact, good titles

You are not trying to rank for noisy phrases like “best Christian coloring book 2026” by stuffing them into every headline. For this brand, trust and clarity beat keyword spam.

## What is already done (Pink House testbed)

Unique page titles and meta descriptions

Canadian English (`lang="en-CA"`)

Canonical URLs (currently pointing at pinkhouse.tech)

Open Graph tags on Home / Shop / Book (nice share previews)

Semantic HTML, image alt text, solid performance basics

## What is still missing (do these in Days 1–14)

| Task | Why it matters |
| --- | --- |
| `robots.txt` | Tells crawlers they may index the site |
| `sitemap.xml` | Helps Google find every important page fast |
| JSON-LD (Organization + Product + WebSite) | Can unlock richer search results (brand, price, availability) |
| Twitter/X card tags | Cleaner previews when links are shared on X |
| Favicon / apple-touch-icon | Trust in browser tabs |
| OG tags on About & Contact | Consistent sharing from every URL |
| One clear H1 on the book page | Cleaner SEO structure |
| Google Search Console + Analytics (or Plausible) | So you can see what people actually find and buy |
| Study-guide landing page | Fresh, useful content Google can index; trust for churches |
| At cutover: flip all canonicals / OG URLs to `lifeofjesus.ca` | Don’t leave Google pointing at the testbed forever |

## Honest expectation

In 60 days, SEO work mainly:

Stops you from looking unfinished to Google

Improves share previews

Starts indexing the comfort site and study guide

It will not by itself create a flood of Christmas buyers. Pair it with the promotion calendar below.

## Keyword / content themes (natural language)

Write pages and posts people would actually search or say:

Life of Jesus coloring book

Christian gift / baptism / confirmation / Advent gift

sacred art coloring / classical Christian art

Caravaggio, Rubens, Last Supper, Nativity

church fundraiser coloring book / parish gift

adult coloring faith / quiet table activity

# 3. Products to push (priority order)

| Priority | Product | Price | Why push it |
| --- | --- | --- | --- |
| 1 | Life of Jesus Coloring Book | $39.99 CAD | Hero product. All traffic should be able to buy this in one click. |
| 2 | LoJ + Last Supper bundle | $54.99 | Best “thoughtful gift” upsell from the book page. |
| 3 | Da Vinci’s Last Supper (table-sized) | $19.99 | Lower-price entry; family table project; good ad / pin bait. |
| 4 | Complete Table Top Trio | $89.99 | Big gift / parish thank-you set. |
| 5 | Old Testament companion | $39.99 | Only after shipping/availability is crystal clear. Do not promote “Availability updating.” |

Primary CTAs to keep repeating:

Shop the book

Gift the bundle

Church & charity inquiries → `pierreoca@gmail.com`

Download the study guide (once live)

# 4. Channels that match this product

| Channel | Role in 60 days | Effort |
| --- | --- | --- |
| Parish / church outreach | Highest trust + proven (Out of the Cold / 17 churches) | Medium — personal emails |
| Pinterest | Evergreen art discovery → gift intent | Low weekly |
| Instagram / Facebook | Show open pages, quiet tables, gift moments | Low–medium |
| Email list (start small) | Study-guide downloads + Advent reminder later | Setup once |
| Catholic / Christian media | You already have Catholic Register proof — reuse it | One pitch pack |
| Google (SEO + Search Console) | Foundation + long game | Technical sprint Week 1–2 |
| Small seasonal ads (optional) | Test $5–15/day on Last Supper / gift creatives in Week 5–8 | Only if creative is ready |

Skip for now (or keep tiny): TikTok trends, broad Google Ads on competitive keywords, influencer blasts without samples.

# 5. Success metrics (keep it simple)

Check these every Friday:

| Metric | 60-day aim |
| --- | --- |
| Site sessions (Pink House or .ca, once tracking is on) | Steady weekly climb; don’t obsess over vanity spikes |
| Add-to-cart / purchases on lifeofjesus.ca | At least a clear weekly sales pulse — book + Last Supper + 1 bundle type |
| Church / charity emails to Pierre | 3–8 serious inquiries in 60 days |
| Study-guide downloads (if gated or tracked) | 25+ |
| Google Search Console | Property verified; sitemap submitted; first impressions appearing |
| Content shipped | Study-guide page + 6 short art posts / pins batches |

If only one number can move: books sold + parish inquiries.

# 6. The 60-day calendar

## Phase A — Days 1–14: Foundation (sell-ready + SEO-ready)

Theme: Make the path to purchase and Google’s first impression clean.

### Week 1 (Days 1–7) — Decisions & hygiene

Phil / Pierre decisions (do these first):

Confirm Mark + Pierre feedback on the Pink House testbed; list must-fix copy tweaks.

Decide study-guide distribution: free sample on site + full guide with purchase (recommended).

Clarify Old Testament status: shippable now, or hide/pre-order until true.

Pick the public face for these 60 days:

- A) Keep selling on Squarespace while Pink House is the “pretty front” people are shown, or

- B) Accelerate cutover of `lifeofjesus.ca` to the comfort site.

Either works — but every promo link you share should go to one consistent URL.

Ops / site tasks:

☐ Add Analytics (GA4 or Plausible) + Google Search Console on the public URL you will promote

☐ Add favicon

☐ Add `robots.txt` + `sitemap.xml`

☐ Add Twitter card tags; finish OG on About & Contact

☐ Fix dual H1 on book page

☐ Confirm every Buy button hits the correct Squarespace product

☐ On Squarespace (if you still have access): remove junk `/home` textile page, fix artist-name typos (Caravaggio / Rubens), remove stale PRE-ORDER labels where stock is live

☐ Write a one-page Parish Partner note (PDF or email body): what the book is, fundraising proof quote, wholesale/bulk ask, Pierre’s email

Content this week:

☐ Draft study-guide landing page copy (one headline, one paragraph, sample lesson blurb, two CTAs)

☐ Export or scan 3–5 best interior pages as pin/post images (warm, readable, not cluttered with text overlays)

Promotion this week:

☐ Soft launch list: 10 people who already love the book → ask them to share the comfort homepage + buy link

☐ Personal thank-you / reconnect emails to past parish contacts (Out of the Cold network, funeral director, any prior bulk buyers)

### Week 2 (Days 8–14) — Study guide + schema + first public push

☐ Publish `/study-guide/` (or equivalent) with sample PDF

☐ Add JSON-LD Product schema for the hero book (+ Organization / WebSite)

☐ Submit sitemap in Search Console

☐ Create Pinterest business account (or polish existing) → board: *Sacred Art to Color*, *Christian Gifts*, *Advent & Christmas Table*

☐ Create 10 Pins from interiors + cover (link half to book page, half to Last Supper / bundle)

☐ Instagram/Facebook: 3 posts — (1) open-page linger, (2) gift framing, (3) Catholic Register / proof quote

☐ Email signature for Phil & Pierre: one line + link to the book

End of Phase A checkpoint: Someone who has never heard of you can land, feel the brand, understand the gift, and buy in under two minutes. Google can crawl the important pages.

## Phase B — Days 15–35: Eyeballs & early sales

Theme: Show the art where gift-minded people already browse; reopen parish doors.

### Week 3 (Days 15–21) — Parish & proof

☐ Send 15–25 parish / program emails (Ontario first): short, warm, attach Parish Partner note + link to study-guide sample

☐ Offer: sample book for serious fundraising conversations (if inventory allows)

☐ Home or About: keep proof quotes near a Buy / Church CTA (already strong — don’t bury them)

☐ One short blog-style page or update: *“Why giant 11×17 sacred art coloring?”* (answers size skepticism; good SEO)

☐ Pinterest: 5 more pins; remix successful creatives

Sales focus: Hero book + church bulk interest. Soft-mention Last Supper as table project.

### Week 4 (Days 22–28) — Gift occasions

☐ Publish a simple Gift occasions reminder in social (baptism, confirmation, sympathy, teacher, Advent prep) — one occasion per post, not a cluttered list in ads

☐ Push the $54.99 LoJ + Last Supper bundle as the default “I need a real gift” option

☐ Collect 3 new short testimonials (even from friends/family who colored a page) — add near product CTAs when you can

☐ Optional: small boost ($5–10/day) on best-performing Facebook/Instagram art post, geo Canada

### Week 5 (Days 29–35) — Media & list

☐ Build a tiny press / media kit folder: cover, 2 interiors, bio paragraph, Catholic Register clip, contact emails

☐ Pitch 3–5 Canadian Christian / local lifestyle outlets (Register follow-up, diocesan papers, community blogs)

☐ If study-guide email capture is on: send Email #1 — thank you + one coloring tip + shop link

☐ Review Search Console: which queries/pages appear? Fix titles if Google is picking weak ones

☐ Clarify and either promote or pause Old Testament based on real availability

End of Phase B checkpoint: Weekly sales pulse exists; at least a few parish conversations are alive; pins/posts are shipping without drama.

## Phase C — Days 36–60: Conversion & Christmas runway

Theme: Turn attention into orders; plant Advent/Christmas demand.

### Week 6 (Days 36–42) — Conversion polish

☐ On book + shop paths: add shipping / returns / what’s in the box in plain language (reduces “almost bought” drop-off)

☐ Put one testimonial on the book page near the Buy button

☐ Retarget warm audience only if ads are already running (site visitors / engagers) with bundle creative

☐ Second parish wave: 10 new contacts + follow-up to non-responders from Week 3 (polite bump)

### Week 7 (Days 43–49) — Advent seed content

☐ Content: *“A quiet Advent table”* — Last Supper + LoJ as December gift / family activity (publish + pin + post)

☐ Offer idea for churches: Advent fundraiser pack (books + suggested pricing + Pierre contact)

☐ Email #2 to list: Advent gift framing + bundle

☐ Refresh top 5 Pins with seasonal board placement (Christmas Gifts, Advent)

### Week 8 (Days 50–60) — Review, double down, plan December

☐ Friday metrics review: what sold? which pin/post/email got replies?

☐ Double down only on winners (usually: art close-ups + gift bundle + parish proof)

☐ Pause anything that took hours and produced silence

☐ Decide December budget: organic-only vs small ad spend

☐ Technical: if cutover to `lifeofjesus.ca` is approved, schedule canonical/OG/DNS flip with a redirect plan from old Squarespace URLs where possible

☐ Write a one-page December sprint note (not this document’s job to finish — just outline gifts, shipping cutoffs, parish Advent offers)

End of Phase C checkpoint: You know your best creative, your best offer (book vs bundle), and you have a short Christmas runway plan — not a mystery.

# 7. Weekly rhythm (so this stays doable)

Do not try to do everything every day. Use this cadence:

| Day | Habit |
| --- | --- |
| Monday | One outreach block (parish emails or follow-ups) — 45–60 min |
| Wednesday | One content ship (pin batch or Instagram/Facebook post or small page update) |
| Friday | 20-minute metrics + buy-button / site sanity check |
| Anytime | Reply fast to church/press emails — those are your warmest leads |

Phil’s role (strategy / site / Cursor): keep the public face beautiful, measurable, and consistent.

Pierre’s role (owner / parish): church conversations, sample books, fundraising offers.

# 8. Ready-to-use message starters

## Parish email (short)

Subject: Sacred art coloring books for your parish fundraiser  
 
Hello [Name],  
 
I’m reaching out about Life of Jesus — giant 11×17 coloring books of classical sacred art (Caravaggio, Rubens, and others).  
 
The Out of the Cold program in St. Catharines used the book across 17 affiliated churches as a fundraising tool. We also have a short study-guide sample if you’d like to evaluate it quietly before any commitment.  
 
If helpful, I can send details or a sample: [link to comfort site / study guide]  
 
Grateful for the work you do,  
Pierre  
pierreoca@gmail.com

## Social caption (art linger)

Familiar scenes. Room to breathe.  
Life of Jesus — the Greatest Story Ever Told, through the greatest art ever made.  
A quiet gift for family tables and parish life.  
[link]

## Bundle caption

Not sure what to give? Start with the book people linger over — then add Da Vinci’s Last Supper for the table.  
Life of Jesus gift bundle · [link]

# 9. Budget guide (keep it modest unless winners appear)

| Item | Suggested |
| --- | --- |
| Tools (Pinterest, Canva, Beehiiv free tier, Search Console) | $0–20/mo |
| Optional social boosts Weeks 4–8 | $5–15/day only on proven creatives |
| Sample books for serious parish leads | Inventory you already have — treat as marketing COGS |
| New website platform fees | Don’t add Stripe/domain complexity in these 60 days unless cutover is already decided |

Rule: Spend time on parish + art content before spending money on ads.

# 10. What *not* to do in these 60 days

Don’t rebuild the whole stack (Stripe, new TLD, full Squarespace wipe) mid-promotion unless Mark/Pierre have approved cutover.

Don’t hide the study guide entirely behind purchase if churches matter.

Don’t promote Old Testament while the site still says availability is unclear.

Don’t stuff keywords into the hero.

Don’t scatter links across five different homepage URLs — pick one public face.

Don’t wait for “perfect SEO” before emailing parishes. Parishes buy from trust and samples.

# 11. Checklist summary (print this page)

## Days 1–14

☐ Mark/Pierre feedback applied

☐ One public URL chosen for all promotion

☐ Analytics + Search Console live

☐ robots, sitemap, favicon, schema, OG gaps fixed

☐ Study-guide sample page live

☐ Parish Partner note written

☐ First pins + 3 social posts shipped

## Days 15–35

☐ 15–25 parish emails sent

☐ Bundle positioned as default gift upsell

☐ Size/Gift content page live

☐ Media kit + a few pitches

☐ Old Testament status resolved

## Days 36–60

☐ Shipping/returns clarity on buy path

☐ Advent/Christmas seed content live

☐ Second parish wave + list email

☐ Metrics review → double down on winners

☐ December runway note drafted

# 12. How this ties back to the design docs

This plan extends `DESIGN-AND-SEO.md`:

Same comfort-first brand rules

Same technical SEO gaps, now scheduled into Weeks 1–2

Same study-guide recommendation, now a concrete launch item

Same Canada / church / gift traffic logic, now a week-by-week calendar aimed at sales, not just a prettier site

The website is beautiful. These 60 days are about letting the right people find it — and buy.

*Prepared for Phil & Pierre from the Pink House Life of Jesus testbed strategy. Save the `.docx` to your laptop (e.g. `C:\LifeOfJesus\`) or open it in Google Docs for easy reading.*